## Status-uptodate (P)
CM's Special Pkg for Barak valley
Phase-I (2013-14)
No. of projects sanctioned = | 85 | Nos.
Sanctioned Amount= | 415.5842 | Cr.
Sanctioned Road Length= | 407.126 | Km
No. of Bridges= | 32 | Nos.
No. of projects awarded = | 85 | Nos.
No. of projects completed = | 32 | Nos.
No. of Bridge Completed= | 4 | Nos.
Road Length Completed(BT/ICBP)= | 253.58 | Km
Uptodate Expenditure= | 228.7502 | Cr.
Phase-II (2014-15 & 2015-16)
No. of projects sanctioned = | 145 | Nos.
Sanctioned Amount= | 287.0127 | Cr.
Sanctioned Road Length= | 414.835 | Km
No. of Bridges= | 17 | Nos.
No. of projects awarded = | 111 | Nos.
[ 34 nos.not yet awarded/dropped/withdrawn (24 nos. of project out of 134 are not yet awarded/dropped/ withdrawn.+Work Withdrawn as road is cosidered as NH=1 no. AA received But not alloted=8, 1 no of rd yet to be started )]
No. of projects completed = | 21 | Nos.
No. of Bridge Completed= | 2 | No.
Road Length Completed(BT/ICBP)= | 93.0138 | Km
Uptodate Expenditure= | 71.3499 | Cr.